## Organization
TuanNQ6
DuongNV7
Team 1 | Team 2 | Testers
DungTM8 | HuyHV | NguyetDTA1
PhucPV6 | TungLD2 | ThaoNT30
ThanhTD12 | TruongTQ4 | HangNT18
ThiND1

## Process
1. Development process
| Step 1: | Develops study requirement & screen design
=> Write note about your understanding
| Step 2: | Developers confirm requirement & screen design understanding with testers, team leaders, BA
=> Meeting memo
| Step 3: | Developers develop presentation layers (JSP, Controller)
| Step 4: | Developers demo GUI, and fix comments from testers, team leader, BA
| Step 5: | Developer continue developing service & repository layers
| Step 6: | Developer demo function with team
| Step 7: | Tester execute testing
| Step 8: | Developer fix bugs and finish function for releasing
Study Requirement
Confirm requirement understanding
Develop presentation layer
Demo GUI
& Update presentation layer
Develop service & repository layers
Demo function
Execute testing
Fix bugs

## TeamRules
Rule 1: | Daily meeting at 9:00 AM everyday
- What did you do yestoday? What is the status of them?
- What are you going to do today?
- Are you on schedule or late? Do you need any action to cover your task?
- Do you have any issue want to share with team?
Rule 2: | Daily report by email at 5:00 PM everyday
| => Subject: |  | [KohYoung_Training][DailyReport] DuongNV7 - Jun 16, 2018
| => To: |  | DuongNV7, TuanNQ6
| => CC: |  | DungTM8, HuyHV, PhucPV6, ThanhTD12, ThiND1, TungLD2, TruongTQ4, NguyetDTA1, HangNT18, ThaoNT30
- Today tasks:
|  | Task name |  | Status | Estimate time | Spent time | Remain time
- Next day tasks:
|  | Task name |  | Status | Estimate time | Remain time
- Issue:
|  | Issue description |  | Status | Assign to | Jira No
Rule 3: | Update task status in Jira

## Requirements
No. | Name | PIC | Tester | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 | Step 8
1 | Manage Building | Team 2 | XoanDT
1.1 | List screen | TruongTQ4 | XoanDT
1.2 | Detail screen | TruongTQ4 | XoanDT
1.3 | Create screen | TruongTQ4 | XoanDT
1.4 | Update screen | TruongTQ4 | XoanDT
1.5 | Import from csv | TungLD2 | XoanDT
1.6 | Export to csv | TungLD2 | XoanDT
2 | Manage products | Team 1 | ThaoNT30
2.1 | List screen | ThanhTD12 | ThaoNT30
2.2 | Detail screen | ThanhTD12 | ThaoNT30
2.3 | Create screen | ThanhTD12 | ThaoNT30
2.4 | Update screen | ThanhTD12 | ThaoNT30
2.5 | Import from csv | ThiND1 | ThaoNT30
2.6 | Export to csv | ThiND1 | ThaoNT30
3 | Manage disaster | Team 2 | HangNT18
3.1 | List screen | HuyHV | HangNT18
3.2 | Detail screen | HuyHV | HangNT18
3.3 | Create screen | HuyHV | HangNT18
3.4 | Update screen | HuyHV | HangNT18
4 | Manage damage | Team 1 | XoanDT
4.1 | List screen | PhucPV6 | XoanDT
4.2 | Detail screen | PhucPV6 | XoanDT
4.3 | Create screen | PhucPV6 | XoanDT
4.4 | Update screen | PhucPV6 | XoanDT
5 | Manage users | Team 1 | ThaoNT30
5.1 | List screen | DungTM8 | ThaoNT30
5.2 | Detail screen | DungTM8 | ThaoNT30
5.3 | Create screen | DungTM8 | ThaoNT30
5.4 | Update screen | DungTM8 | ThaoNT30